Enerwave - ETL Pipeline Status Sync

Wednesday, May 13, 2026, 10:00 AM (EEST)

Transcript

Christina Latroni   0:00:05

Good morning everyone, thanks for joining the ETL status review.

Christina Latroni   0:00:14

We have four items on the agenda — source ingestion progress, the transformation layer, data quality checks, and the go-live timeline.

Eleni Antoniou   0:00:28

Morning Christina. I have a hard stop at the half-hour for an internal meeting.

Christina Latroni   0:00:36

Noted. Yannis, please walk us through the source ingestion progress.

Yannis Papadakis   0:00:46

Right, so we have completed connectivity to four of the six planned source systems.

Yannis Papadakis   0:00:56

The two remaining are the legacy operational database and the third-party billing API.

Yannis Papadakis   0:01:08

The operational database needs a service account from your infrastructure team. The billing API is blocked on a contract amendment.

Nikos Papadopoulos   0:01:24

I will request the service account today and have it provisioned by Friday.

Nikos Papadopoulos   0:01:34

On the billing API contract, procurement is reviewing this week. I expect sign-off by next Wednesday.

Christina Latroni   0:01:46

OK. If the contract slips beyond next Wednesday, we need a workaround — possibly a manual CSV drop in the interim.

Eleni Antoniou   0:02:00

Agreed. A manual CSV drop is acceptable for the first two weeks post go-live if needed.

Yannis Papadakis   0:02:14

On the transformation layer, we have implemented eighteen of the twenty-two business rules.

Yannis Papadakis   0:02:26

The four remaining are complex aggregations that need confirmation from your finance team.

Eleni Antoniou   0:02:38

I will arrange a session with the finance controller for Monday morning.

Christina Latroni   0:02:48

Monday works. Yannis, please prepare a one-pager with the four open rules and the proposed logic so we can validate quickly.

Yannis Papadakis   0:03:02

Will send the one-pager by end of day tomorrow.

Christina Latroni   0:03:12

On data quality — we discussed last week introducing a row-count and null-rate check at each stage.

Yannis Papadakis   0:03:22

Implemented. The checks run after each pipeline execution and write to a monitoring table.

Yannis Papadakis   0:03:32

First production-like run completed yesterday with no critical failures.

Christina Latroni   0:03:42

Excellent. Please share the monitoring dashboard with Eleni and Nikos this afternoon.

Yannis Papadakis   0:03:52

Will do.

Nikos Papadopoulos   0:04:00

One concern from our side — incremental load performance during the overnight window.

Nikos Papadopoulos   0:04:10

The full load takes around four hours. We need incremental loads completing within ninety minutes.

Yannis Papadakis   0:04:22

Current incremental load benchmarks at sixty minutes on production-equivalent volumes. Within target.

Christina Latroni   0:04:34

Good. Let us flag the four-hour full-load as a risk to monitor — if data volume doubles, we may exceed the window.

Christina Latroni   0:04:50

Last item — the go-live date. We are still tracking for the twenty-eighth of May.

Eleni Antoniou   0:05:00

From our side, business sign-off is expected by the twenty-second.

Christina Latroni   0:05:10

Then May the twenty-eighth remains the target. Yannis, please prepare a cutover checklist and share by next Tuesday.

Yannis Papadakis   0:05:22

Will prepare and share by Tuesday.

Christina Latroni   0:05:32

Anything else? OK, thanks everyone. Eleni, please drop when you need to.

Eleni Antoniou   0:05:42

Thanks Christina, talk Monday.